## Incident Log
AI Incident Log
Log every suspected AI-related incident, regardless of severity or whether it met the regulatory serious-incident threshold.
Incident ID | System ID | Date Identified | Description | Severity | Serious Incident? (Y/N) | Regulatory Notification Required? | Notification Deadline | Containment Action | Root Cause | Remediation Status | Closed Date
INC-001 | ORG-AI-001 | 2026-04-12 | Credit model bias audit flagged disparate approval rate for one demographic group | Sev 2 | N | N | N/A | Model paused for affected segment pending investigation | Training data underrepresented segment in recent quarters | In Progress
INC-002 | ORG-AI-006 | 2026-02-03 | Voice biometric authentication bypassed via synthetic voice sample in penetration test | Sev 1 | Y | Y | 2026-02-18 | Liveness detection deployed same day; affected auth method disabled temporarily | Liveness detection was not enabled by default at rollout | Closed | 2026-03-01

## Severity Definitions
Severity Definitions
Severity | Definition
Sev 1 | Death, serious injury, critical infrastructure disruption, or fundamental rights infringement — likely meets EU AI Act 'serious incident' definition
Sev 2 | Significant harm to individuals or material regulatory exposure, not yet confirmed as a serious incident
Sev 3 | Limited, recoverable harm or a near-miss with no confirmed individual impact
Sev 4 | Minor operational issue with no rights, safety, or compliance implication