AI Governance Implementation Roadmap

Core Toolkit — Foundational Document 7 of 8 (narrative companion to the roadmap workbook)

Doc ID: AIGV-CORE-007 · Version 1.0

Disclaimer

This document is a portfolio artefact created for demonstration and educational purposes only. It does not represent the policies, systems, or practices of any real organisation, and no organisation, vendor, or individual named or implied within it refers to an actual entity. All identifiers (e.g. ORG-AI-0XX) are fictional and used solely to illustrate a coherent governance scenario. This template does not constitute legal advice and should not be relied upon for regulatory compliance without review by qualified counsel and subject-matter experts.

Karun· AIGP (AI Governance Professional)

# 1. Purpose

This document describes a phased, four-quarter approach to standing up an AI governance program from a zero or low baseline. It is designed to be read alongside the companion workbook (AIGV-CORE-007-Roadmap.xlsx), which tracks phase tasks, owners, dates, and status.

# 2. Phasing Overview

| Phase | Timeframe | Primary objective |
| --- | --- | --- |
| Phase 1 — Foundation | Weeks 1–6 | Establish governance structure, approve Framework and Policy, begin inventory build |
| Phase 2 — Discovery & Classification | Weeks 5–12 | Complete AI system inventory, classify by risk tier, identify high-risk backlog |
| Phase 3 — Controls Build-Out | Weeks 10–20 | Stand up conformity documentation process, human oversight procedures, incident response |
| Phase 4 — Operationalise & Mature | Weeks 18–26 and ongoing | Quarterly review cadence, maturity assessment baseline, committee reporting rhythm |

# 3. Phase 1 — Foundation (Weeks 1–6)

- Secure executive sponsor and confirm AI Governance Committee membership.

- Draft and approve the AI Governance Framework and AI Policy (Committee sign-off).

- Stand up the AI Governance Office (may initially be a single accountable lead).

- Communicate the Policy organisation-wide and open the intake channel for new AI use cases.

- Begin populating the AI System Inventory from known systems and procurement records.

# 4. Phase 2 — Discovery & Classification (Weeks 5–12)

- Run a structured discovery exercise: procurement records, IT asset register, vendor contract review, and a business-unit self-declaration survey to surface shadow AI.

- Complete AI Use Case Assessment Forms for all discovered systems.

- Apply the risk classification model; flag unacceptable-risk use for immediate remediation.

- Build the initial high-risk backlog and sequence it for Phase 3 conformity work.

# 5. Phase 3 — Controls Build-Out (Weeks 10–20)

- Develop conformity documentation templates (technical documentation, risk management file, human oversight procedure, instructions for use) for high-risk systems.

- Stand up the incident response and regulatory escalation procedure, including severity definitions and escalation paths.

- Define human oversight control points for each high-risk system and confirm named override authority.

- Deliver initial training to business owners, technical owners, and the Committee on their governance responsibilities.

# 6. Phase 4 — Operationalise & Mature (Weeks 18–26+)

- Launch the quarterly governance review cycle for high- and limited-risk systems.

- Run the first AI Governance Maturity Assessment to establish a baseline score across domains.

- Establish the Committee's standing quarterly reporting package to executive leadership.

- Set a 6–12 month re-assessment cycle to track maturity progression and refresh the roadmap for the next horizon.

# 7. Critical Success Factors

- Executive sponsorship visible from Phase 1 — governance stalls without a mandate from the top.

- Proportionate controls — over-engineering minimal-risk system requirements erodes business buy-in.

- Single source of truth — the inventory must be the authoritative record referenced by procurement, legal, and audit.

- Iterative rollout — Phase 3 controls can be piloted on 1–2 high-risk systems before scaling organisation-wide.

# 8. How to Use the Companion Workbook

The workbook (AIGV-CORE-007-Roadmap.xlsx) breaks each phase into discrete tasks with owner, target start/end dates, dependency notes, and a status field (Not Started / In Progress / Blocked / Complete). Progress percentage is calculated automatically from task status. Update the workbook at each Committee meeting to keep the roadmap current.