## Roadmap Tasks
Phase | Task | Owner | Target Start | Target End | Status | % Weight | Dependency / Notes
Phase 1 — Foundation | Secure executive sponsor and confirm Committee membership | AI Governance Lead | Week 1 | Week 2 | Complete | 5
Phase 1 — Foundation | Draft and approve AI Governance Framework | AI Governance Lead | Week 1 | Week 4 | Complete | 5
Phase 1 — Foundation | Draft and approve AI Policy | AI Governance Lead | Week 2 | Week 5 | In Progress | 5 | Depends on Framework approval
Phase 1 — Foundation | Stand up AI Governance Office | Executive Sponsor | Week 2 | Week 6 | In Progress | 5
Phase 1 — Foundation | Open intake channel and communicate Policy org-wide | AI Governance Lead | Week 5 | Week 6 | Not Started | 5
Phase 2 — Discovery & Classification | Run structured discovery (procurement, IT asset register, vendor review) | AI Governance Office | Week 5 | Week 9 | Not Started | 8
Phase 2 — Discovery & Classification | Business-unit self-declaration survey for shadow AI | AI Governance Office | Week 6 | Week 9 | Not Started | 6
Phase 2 — Discovery & Classification | Complete Use Case Assessment Forms for discovered systems | Business Owners | Week 8 | Week 11 | Not Started | 8 | Depends on discovery
Phase 2 — Discovery & Classification | Apply risk classification model; build high-risk backlog | AI Governance Office | Week 10 | Week 12 | Not Started | 6
Phase 3 — Controls Build-Out | Develop conformity documentation templates | AI Governance Office | Week 10 | Week 14 | Not Started | 8
Phase 3 — Controls Build-Out | Stand up incident response & escalation procedure | AI Governance Office + Legal | Week 12 | Week 16 | Not Started | 8
Phase 3 — Controls Build-Out | Define human oversight control points per high-risk system | Technical Owners | Week 13 | Week 18 | Not Started | 6 | Depends on backlog
Phase 3 — Controls Build-Out | Deliver role-based training to owners and Committee | AI Governance Office | Week 16 | Week 20 | Not Started | 5
Phase 4 — Operationalise & Mature | Launch quarterly governance review cycle | AI Governance Office | Week 18 | Week 20 | Not Started | 6
Phase 4 — Operationalise & Mature | Run baseline Maturity Assessment | AI Governance Office | Week 20 | Week 22 | Not Started | 6
Phase 4 — Operationalise & Mature | Establish Committee quarterly reporting package | AI Governance Lead | Week 22 | Week 24 | Not Started | 5
Phase 4 — Operationalise & Mature | Set 6–12 month re-assessment cycle and refresh roadmap | AI Governance Committee | Week 24 | Week 26 | Not Started | 5

## Progress Dashboard
Implementation Progress
Overall Weighted Progress (%) | 9.804%
Phase | Tasks | Complete | % Complete
Phase 1 — Foundation | 5 | 2 | 40%
Phase 2 — Discovery & Classification | 4 | 0 | 0%
Phase 3 — Controls Build-Out | 4 | 0 | 0%
Phase 4 — Operationalise & Mature | 4 | 0 | 0%