## Risk Register
ISO 42001 — Risk and Opportunity Register (Clause 6.1)
ID | Type | Description | Likelihood (1-5) | Impact (1-5) | Score | Rating | Treatment/Action | Owner | Target Date | Status
R-001 | Risk | AI model performance degrades undetected between review cycles | 3 | 4 | 12 | High | Implement continuous monitoring thresholds; tie to Quarterly Governance Review |  |  | In Progress
R-002 | Risk | Third-party foundation model provider changes model behaviour without notice | 3 | 3 | 9 | High | Add change-notification clause to vendor contracts; version-pin where possible |  |  | Open
R-003 | Risk | AIMS scope excludes shadow AI tools adopted informally by business units | 4 | 3 | 12 | High | Run structured discovery exercise; add self-declaration channel |  |  | Open
O-001 | Opportunity | AIMS certification differentiates the organisation in vendor RFPs | 3 | 3 | 9 | High | Highlight certification status in sales/procurement materials once achieved |  |  | Open
O-002 | Opportunity | Mature AIMS reduces duplicate effort across EU AI Act, and other jurisdiction-specific compliance work | 4 | 4 | 16 | Critical | Map AIMS outputs directly to jurisdiction-specific obligations via the Regulatory Crosswalk |  |  | Open