## Risk Register
AI Risk Register
Risk score and rating auto-calculate from Likelihood x Impact. See AI Risk Assessment Methodology (RISK-001) for scoring definitions.
Risk ID | System ID | Risk Category | Description | Likelihood (1-5) | Impact (1-5) | Score | Rating | Treatment Strategy | Treatment Action | Owner | Status | Review Date
RISK-001 | ORG-AI-001 | Fairness/Bias | Credit model may systematically disadvantage applicants in a protected group | 3 | 4 | 12 | High | Mitigate | Quarterly disparate-impact testing across protected classes | ML Engineering Lead | Open
RISK-002 | ORG-AI-003 | Performance | AML monitoring model under-flags novel laundering typologies not in training data | 3 | 5 | 15 | High | Mitigate | Backtest against known cases quarterly; add typology-specific rules as supplement | Data Science Lead | Open
RISK-003 | ORG-AI-005 | Fairness/Bias | Recruitment screening tool may use proxy features correlated with protected characteristics | 3 | 4 | 12 | High | Mitigate | Independent bias audit annually; test specifically for proxy discrimination | HR Systems Lead | In Progress
RISK-004 | ORG-AI-006 | Security | Voice biometric system vulnerable to synthetic voice spoofing | 2 | 5 | 10 | High | Mitigate | Add liveness detection; monitor for anomalous authentication patterns | Security Engineering Lead | Open
RISK-005 | ORG-AI-002 | Third-Party/Vendor | Vendor A chatbot model updates without advance notice, risking behaviour drift | 3 | 3 | 9 | Medium | Transfer | Add change-notification clause to vendor contract renewal | Platform Engineering Lead | Open